## Backlog
Group: A |  |  |  |  | Last update: 24.05.2021
# | Task | Result | Responsible | Support by | Planned for Sprint # | Planned Effort in h | Realized in Sprint # | Real Effort in h
1 | Creating a Discord Server for the Group | Voice communication & Filesharing | Karsten Rudolf | Team | 0 | 5min | 1 | 5min
2 | Creating a WhatsApp Group | Text communication & organising meetings | Edgar Meilinger | Team | 0 | 2min | 1 | 2min
3 | Getting all phone numbers from teammembers for inviting them | Having phone numbers for the WhatsApp Group | Ersan Ünsal | Team | 0 | 0.5 | 1 | 1
4 | Setting up a first meeting in Discord | Get to know each other | Jan Leonardi | Team | 0 | 0.5 | 1 | 0.5
5 | What development enviroment do we use ? | all have the same development enviroment | Amine Amzil | Team | 0 | 0.5 | 1 | 0.5
6 | First meeting: What VCS do we use ? | sharing code & version controlling | Ersan Ünsal | Team | 0 | 0.5 | 1 | 0.5
7 | Setting up the VCS (GitHub) | sharing code & version controlling | Ersan Ünsal | Team | 0 | 1 | 1 | 1
8 | getting started with node.js, express, GoJS | understanding node.js, express, GoJS | Karsten Rudolf | Team | 0 | 6 | 1 | 6
9 | Building a MindMap for the project | Getting an overview for what we have so far (will be extended in the future) | Gökhan Ünsal | Team | 0 | 0.5 | 1 | 0.5
10 | Display Application - Canvas | Visual Background Canvas | Jan Leonardi | Karsten Rudolf, Edgar Meilinger | 1 | 2 | 1 | 1
11 | Display Application - Symbols | Symbols can be created in the application | Jan Leonardi | Karsten Rudolf, Edgar Meilinger | 1 | 3 | 1 | 3
12 | Display Application - Movement | Elements can be moved freely in the application | Jan Leonardi | Karsten Rudolf, Ersan Ünsal | 1 | 1 | 1 | 1
13 | Display Application - Symbol Palette | Symbols can be dragged and dropped from the palette to the Main | Ersan Ünsal | Edgar Meilinger, Jan Leonardi | 1 | 2 | 1 | 2
14 | Display Application - CSS Design | Application Design | Karsten Rudolf | Jan Leonardi, Ersan Ünsal | 1 | 6 | 1 | 5
15 | Application properties - Application documentation | Basic documentation linked page for the customer | Ersan Ünsal | Edgar Meilinger | 1 | 2 | 1 | 2
16 | Application properties - properties window (name, version, description, COTS, release date, shutdown date) | The properties can be shown using a properties window | Edgar Meilinger | Jan Leonardi, Gökhan Ünsal | 1 | 4 | 1 | 4
17 | Dataflows - Application linking | Applications can be connected with directed associations (arrowheads) representing dataflows. | Amine Amzil | Gökhan Ünsal, Ersan Ünsal | 1 | 6 | 1 | 6
18 | Data objects | With following properties: Name, description & personal data ? Dataflow refers to Data Object | Amine Amzil | Edgar Meilinger | 2 | 4 | 2 | 4
19 | Data objects design | Label is like a node; display name, description & personal data | Amine Amzil | Gökhan Ünsal | 2 | 6 | 2 | 6
20 | Rename program to application | Application will appear as default by the name "Application" and not as "Program" | Karsten Rudolf | Edgar Meilinger | 2 | 1 | 2 | 1
21 | Properties dialog windows is only visiable when clicked on (non selection = no properties window) | Properties dialog will only be visible when you click on the Application | Jan Leonardi | Karsten Rudolf | 2 | 2 | 2 | 2
22 | Link property windows shows only "name" and "color" in property window | Property window for links will only show "name" & "color" | Amine Amzil | Jan Leonardi | 2 | 2 | 2 | 2
23 | Research for: traffic light signals | Gathering information about how GoJS saves data to use it for the traffic light | Karsten Rudolf | Ersan Ünsal | 2 | 3 | 2 | 3
24 | Application: traffic light signals for release / shutdown date (blue = default, red = past shutdown date, amber = release date in future, green = in time between release & shutdown date) | Implementing traffic light system for Applications the have a visual overview for the status | Ersan Ünsal | Karsten Rudolf | 2 | 5 | 2 | 5
25 | 3 dropdowns values for Cots: cots, propietary, undefined | Changing free text value for COTS into a dropdown menu with 3 values(cots, propietary, undefined) | Karsten Rudolf | Ersan Ünsal | 2 | 3 | 2 | 3
26 | Research for: Fields of decription a bit longer, several lines visible | Change input filed to textarea | Edgar Meilinger | Jan Leonardi | 2 | 3 | 2 | 3
27 | Graphical symbol for applications: applications need to be shown by a rectangle with two additional lines (as in the initial slide deck). | Changing the visual desgin of the symbol for the applications | Edgar Meilinger | Ersan Ünsal | 2 | 4 | 2 | 4
28 | Research: How to export files with GoJS | Being able to solve the export tasks | Jan Leonardi | Amine Amzil | 2 | 6 | 2 | 6
29 | Error Research: Output diagram object | Diagramm data can be shown as JSON | Ersan Ünsal | Jan Leonardi | 2 | 3 | 2 | 3
30 | Report data objects: A report is required so that all data objects in the application landscape can be exported as an file (csv). | Implenting an export option to save & report all data objects in the application landscape as an .csv file | Jan Leonardi | Amine Amzil | 2 | 4 | 2 | 4
31 | Setting up database and connection to the app | Communication between app and database | Ersan Ünsal | Karsten Rudolf | 2 | 3 | 2 | 3
32 | Persistent storage | Application landscape has to be stored persistently e.g. as Database or JSON file | Ersan Ünsal | Karsten Rudolf | 3 | 8
33 | Data import: There is an Excel file with existing applications. They need to be imported into the graphical editor, so that the additional applications are shown on the canvas. | Implementing an import option for excel files so you can see them on the canvas | Amine Amzil | Ersan Ünsal | 3 | 6
34 | Fields of decription a bit longer, several lines visible | Implementing more visible lines in the fields of description | Edgar Meilinger | Jan Leonardi | 3 | 3
35 | Report applications working with personal data: A report needs to be created that lists any application that works with personal data. | Implenting an export option to save & report all data in the application related with personal data | Karsten Rudolf | Jan Leonardi | 3 | 4
36 | Rename the Status to COTS Label | Changing visual text from status to COTS | Ersan Ünsal | Edgar Meilinger | 3 | 1 | 3 | 1
37 | Make Data Object reusable | Reusing an existing Data Object, attached to different line | Karsten Rudolf | Amine Amzil | 3 | 8
38 | Refactoring the Code | Implenting new features | Jan Leonardi | Ersan Ünsal | 3 | 20

## Risks
# | Risk | Mitigation action | Responsible | Status
1 | Problems with Group coordination (for example: group member doesn't show up to team meetings ) | Making sure to have a good communication | Karsten Rudolf
2 | People don't work on their assigned tasks (misunderstandings or lazyness) | Making sure every task is in the backlog with the assigned person | Gökhan Ünsal
3 | Miscalculation in time management | Integrating a timeline for each leg / task | Jan Leonardi
4 | Technical difficulties | helping each other out or trying to find a solution as a team | Ersan Ünsal
5 | Language difficulties | helping each other out or trying to find a solution as a team | Karsten Rudolf
6 | Programming difficulties (different skills in programming or less experience) | helping each other out or trying to find a solution as a team (for example: YouTube tutorials, GitHub…) | Jan Leonardi
7 | A group member is getting ill or has to step back for longterm | Informing the supervisor and ask for further instructions | Edgar Meilinger
8 | Time won't be enough to fulfill the task (if we know it in advance) | Responsible person for task informs team, if the team can't find a solution -> inform supervisor | Gökhan Ünsal
9 | The application of Gökhan Ünsal will be declined | workload has to be divided on 5 people | Gökhan Ünsal
10
11
12
13
14
15
16
17
18
19
20
21

## Param (hidden)
Sprint # | Status | Risk Status
1 | Initial | Open
2 | Started | Issue
3 | Cancelled | Closed
4 | Done