## Backlog
Group: A |  |  |  |  | Last update: 24.05.2021
# | Task | Result | Responsible | Support by | Planned for Sprint # | Planned Effort in h | Realized in Sprint # | Real Effort in h
1 | Creating a Discord Server for the Group | Voice communication & Filesharing | Karsten Rudolf | Team | 0 | 5min | 1 | 5min
2 | Creating a WhatsApp Group | Text communication & organising meetings | Edgar Meilinger | Team | 0 | 2min | 1 | 2min
3 | Getting all phone numbers from teammembers for inviting them | Having phone numbers for the WhatsApp Group | Ersan Ünsal | Team | 0 | 0.5 | 1 | 1
4 | Setting up a first meeting in Discord | Get to know each other | Jan Leonardi | Team | 0 | 0.5 | 1 | 0.5
5 | What development enviroment do we use ? | all have the same development enviroment | Amine Amzil | Team | 0 | 0.5 | 1 | 0.5
6 | First meeting: What VCS do we use ? | sharing code & version controlling | Ersan Ünsal | Team | 0 | 0.5 | 1 | 0.5
7 | Setting up the VCS (GitHub) | sharing code & version controlling | Ersan Ünsal | Team | 0 | 1 | 1 | 1
8 | getting started with node.js, express, GoJS | understanding node.js, express, GoJS | Karsten Rudolf | Team | 0 | 6 | 1 | 6
9 | Building a MindMap for the project | Getting an overview for what we have so far (will be extended in the future) | Gökhan Ünsal | Team | 0 | 0.5 | 1 | 0.5
10 | Display Application - Canvas | Visual Background Canvas | Jan Leonardi | Karsten Rudolf, Edgar Meilinger | 1 | 2 | 1 | 1
11 | Display Application - Symbols | Symbols can be created in the application | Jan Leonardi | Karsten Rudolf, Edgar Meilinger | 1 | 3 | 1 | 3
12 | Display Application - Movement | Elements can be moved freely in the application | Jan Leonardi | Karsten Rudolf, Ersan Ünsal | 1 | 1 | 1 | 1
13 | Display Application - Symbol Palette | Symbols can be dragged and dropped from the palette to the Main | Ersan Ünsal | Edgar Meilinger, Jan Leonardi | 1 | 2 | 1 | 2
14 | Display Application - CSS Design | Application Design | Karsten Rudolf | Jan Leonardi, Ersan Ünsal | 1 | 6 | 1 | 5
15 | Application properties - Application documentation | Basic documentation linked page for the customer | Ersan Ünsal | Edgar Meilinger | 1 | 2 | 1 | 2
16 | Application properties - properties window (name, version, description, COTS, release date, shutdown date) | The properties can be shown using a properties window | Edgar Meilinger | Jan Leonardi, Gökhan Ünsal | 1 | 4 | 1 | 4
17 | Dataflows - Application linking | Applications can be connected with directed associations (arrowheads) representing dataflows. | Amine Amzil | Gökhan Ünsal, Ersan Ünsal | 1 | 6 | 1 | 6
18 | Data objects | With following properties: Name, description & personal data ? Dataflow refers to Data Object | Amine Amzil | Edgar Meilinger | 2 | 4 | 2 | 4
19 | Data objects design | Label is like a node; display name, description & personal data | Amine Amzil | Gökhan Ünsal | 2 | 6 | 2 | 6
20 | Rename program to application | Application will appear as default by the name "Application" and not as "Program" | Karsten Rudolf | Edgar Meilinger | 2 | 1 | 2 | 1
21 | Properties dialog windows is only visiable when clicked on (non selection = no properties window) | Properties dialog will only be visible when you click on the Application | Jan Leonardi | Karsten Rudolf | 2 | 2 | 2 | 2
22 | Link property windows shows only "name" and "color" in property window | Property window for links will only show "name" & "color" | Amine Amzil | Jan Leonardi | 2 | 2 | 2 | 2
23 | Research for: traffic light signals | Gathering information about how GoJS saves data to use it for the traffic light | Karsten Rudolf | Ersan Ünsal | 2 | 3 | 2 | 3
24 | Application: traffic light signals for release / shutdown date (blue = default, red = past shutdown date, amber = release date in future, green = in time between release & shutdown date) | Implementing traffic light system for Applications the have a visual overview for the status | Ersan Ünsal | Karsten Rudolf | 2 | 5 | 2 | 5
25 | 3 dropdowns values for Cots: cots, propietary, undefined | Changing free text value for COTS into a dropdown menu with 3 values(cots, propietary, undefined) | Karsten Rudolf | Ersan Ünsal | 2 | 3 | 2 | 3
26 | Research for: Fields of decription a bit longer, several lines visible | Change input filed to textarea | Edgar Meilinger | Jan Leonardi | 2 | 3 | 2 | 3
27 | Graphical symbol for applications: applications need to be shown by a rectangle with two additional lines (as in the initial slide deck). | Changing the visual desgin of the symbol for the applications | Edgar Meilinger | Ersan Ünsal | 2 | 4 | 2 | 4
28 | Research: How to export files with GoJS | Being able to solve the export tasks | Jan Leonardi | Amine Amzil | 2 | 6 | 2 | 6
29 | Error Research: Output diagram object | Diagramm data can be shown as JSON | Ersan Ünsal | Jan Leonardi | 2 | 3 | 2 | 3
30 | Report data objects: A report is required so that all data objects in the application landscape can be exported as an file (csv). | Implenting an export option to save & report all data objects in the application landscape as an .csv file | Jan Leonardi | Amine Amzil | 2 | 4 | 2 | 4
31 | Setting up database and connection to the app | Communication between app and database | Ersan Ünsal | Karsten Rudolf | 2 | 3 | 2 | 3
32 | Fields of decription a bit longer, several lines visible | Implementing more visible lines in the fields of description | Edgar Meilinger | Jan Leonardi | 2 | 3 | 3 | 3
33 | Report applications working with personal data: A report needs to be created that lists any application that works with personal data. | Implenting an export option to save & report all data in the application related with personal data | Karsten Rudolf | Jan Leonardi | 3 | 3 | 3 | 2
33.1 | Debugging | Fixing bugs | Jan Leonardi | Karsten Rudolf | 3 | 2 | 3 | 2
33.2 | Download component | Download component | Jan Leonardi | Karsten Rudolf | 3 | 1 | 3 | 1
33.3 | Time component | Time component | Jan Leonardi | Karsten Rudolf | 3 | 2 | 3 | 2
34 | Rename the Status to COTS Label | Changing visual text from status to COTS | Ersan Ünsal | Edgar Meilinger | 3 | 1 | 3 | 1
35 | Refactoring the Code | Application landscape has to be stored persistently e.g. as Database
35.1 | Research for MVC-Pattern in NodeJs | Using a Module for MVC Pattern | Ersan Ünsal | Amine Amzil | 3 | 1 | 3 | 1
35.2 | Creating a plan for refactoring | Organising for the tasks to refactor the code | Ersan Ünsal | Amine Amzil | 3 | 2 | 3 | 2
35.3 | Generating a MVC Skeleton | MVC folder hierarchy | Edgar Meilinger | Ersan Ünsal | 3 | 2 | 3 | 2
35.4 | Integrate our GoJS code to the new environment | Code before refactoring works in new Pattern | Edgar Meilinger | Ersan Ünsal | 3 | 3 | 3 | 4
35.5 | Create models for our diagram | Diagram generates objects | Ersan Ünsal | Karsten Rudolf | 3 | 3 | 3 | 3
35.6 | Create routes and controllers | URL-handling Code | Amine Amzil | Edgar Meilinger | 3 | 3 | 3 | 3
35.7 | Testing communication with MongoDB | Diagrams can be loaded and saved persistently in the Database
35.7.1 | Implenting upload to database | Upload to database available | Ersan Ünsal | Edgar Meilinger | 3 | 6 | 3 | 5
35.7.2. | Downloading from database | Download to database available | Edgar Meilinger | Ersan Ünsal | 3 | 2 | 3 | 2
36 | Make Data Object reusable | Reusing an existing Data Object, attached to different line
36.1 | Research for making Data Object reusable | Evaluate in which ways we can implent this task | Jan Leonardi | Karsten Rudolf | 3 | 3 | 3 | 3
36.2 | Implenting a function to read and save all Data Objects and its values | Making sure that we can work with the Data Objects and its values | Karsten Rudolf | Jan Leonardi | 3 | 3 | 3 | 2
36.3 | Add this function into the listener and making sure it won't save duplicates | Add this function into the listener and making sure it won't save duplicates | Karsten Rudolf | Jan Leonardi | 3 | 2 | 3 | 2
36.4 | Function to read and save Data Objects by name | Function to read and save Data Objects by name | Jan Leonardi | Karsten Rudolf | 3 | 3 | 3 | 3
36.5 | Implenting dropdown option for loading presets (Data Objects by name) | Implenting dropdown option for loading presets (Data Objects by name) | Karsten Rudolf | Jan Leonardi | 3 | 2 | 3 | 2
36.6 | Implenting function into listener to fill Data Objects with the selected values from preset | Implenting function into listener to fill Data Objects with the selected values from preset | Karsten Rudolf | Jan Leonardi | 3 | 3 | 3 | 3
37 | Data import: There is an Excel file with existing applications. They need to be imported into the graphical editor, so that the additional applications are shown on the canvas. | Implementing an import option for excel files so you can see them on the canvas
37.1 | Upload function | Excel file can be uploaded temporaly into Server | Amine Amzil | Edgar Meilinger | 3 | 4 | 3 | 3
37.2 | Data cleaning | All rows in the table which contains empty cells should be ignored and not converted to Application Object | Amine Amzil | Jan Leonardi | 3 | 5 | 3 | 6
37.3 | Add the imported apps to the diagram | Imported Application should be added and shown in the diagram | Amine Amzil | Karsten Rudolf | 3 | 2 | 3 | 2
38 | Making DataObjects resuable and multiable DataObjects for each link
38.1 | Refactoring for multiple DataObjects | Refactoring to be able to implement multiple DataObjects | Jan Leonardi | Ersan Ünsal | 4 | 4 | 4 | 6
38.2 | Load and edit Data Objects | Visualized as table so you can choose and edit from this table | Jan Leonardi | Edgar Meilinger | 4 | 4 | 4 | 5
38.3 | Delete DataObjects | Being able to choose DataObjects from table and delete it | Jan Leonardi | Karsten Rudolf | 5 | 2
38.4 | Editing design for table etc. | Make UI more userfriendly | Karsten Rudolf | Jan Leonardi | 5 | 4
38.5 | Refactor CSV export | Export to CSV has to be refactored | Jan Leonardi | Karsten Rudolf | 5 | 5
39 | Rename Preset into customer terms (Reusable Data Objects) | Rename Preset into costumer terms (Reusable Data Objects) | Edgar Meilinger | Amine Amzil | 4 | 1 | 4 | 1
40 | Customising User Interface
40.1 | Rearranging Import- / Export- / Save- and Loadbuttons | Making the UI more User friendly | Karsten Rudolf | Jan Leonardi | 4 | 4 | 4 | 5
40.2 | Research for creating own Data Inspector | Finding a way to implement our own Data Inspector | Karsten Rudolf | Ersan Ünsal | 4 | 2 | 4 | 2
40.3 | Creating our own window and replacing inspector for Data Objects | Making the UI more User friendly | Karsten Rudolf | Jan Leonardi | 4 | 3 | 4 | 3
40.3.1 | Editing design for our own Data Inspector | Making the UI more User friendly | Karsten Rudolf | Ersan Ünsal | 4 | 1 | 4 | 1
40.4 | Greeting Screen | Options to select Diagrams from the database (as a list), creating a new diagram or import diagram from Excel/csv | Ersan Ünsal | Amine Amzil | 4 | 3 | 4 | 4
41 | Option for saving and loading multiple diagrams from the Database | Diagrams have their own unique keys, so they can be loaded and saved from/into the database | Ersan Ünsal | Edgar Meilinger | 4 | 5 | 4 | 4
42 | Customising Excel import window
42.1 | User doesn't need to fill out each tabs -> dropdown option with preloaded values | Mitigation of User errors and more user friendly | Amine Amzil | Edgar Meilinger | 4 | 4
42.2 | Error report list for the failed to import data | Getting information of the Data that didn't get imported | Amine Amzil | Edgar Meilinger | 4 | 4 | 4 | 4
43 | Research: Multiple data objects for each data flow ( How many are possible ? ) | Checking if its possible | Edgar Meilinger | Jan Leonardi | 4 | 4 | 4 | 4
43 | Research: Automated mapping/layout for the diagram | Checking if its possible | Edgar Meilinger | Karsten Rudolf | 4 | 4 | 4 | 4
44 | Refactoring html into pug for views | Frontend is now fully unified over controllers | Edgar Meilinger | Ersan Ünsal | 4 | 3 | 4 | 3
45 | Database form in the UI | Database Credentials are accessable in the application | Ersan Ünsal | Jan Leonardi | 4 | 4 | 4 | 5
46 | Research: Preset for excelsheets with same names | Preset for excelsheets with same names | Amine Amzil | Jan Leonardi | 4 | 3 | 4 | 2
47 | Automatic layout for nodes and bindings | Making the UI more User friendly | Edgar Meilinger | Amine Amzil | 4 | 5 | 4 | 4
48 | Making the UI more consistent for all data object functions | Easier to understand for the customer (button names etc.) | Jan Leonardi | Karsten Rudolf | 5 | 4
49 | Editing the inspector
49.1 | Scaleable window | Window should scale with text sizes | Karsten Rudolf | Ersan Ünsal | 5 | 3
49.2 | Exclude save changes button | Data Objects should only be able to edit due edit function on manage objects sidebar | Karsten Rudolf | Ersan Ünsal | 5 | 2
49.3 | Filling the empty space on the sides | Not wasting space of our window | Karsten Rudolf | Jan Leonardi | 5 | 2
49.4 | Editing design | Making UI more user friendly | Karsten Rudolf | Ersan Ünsal | 5 | 4
50 | Fixing edit function for Data Objects | Fixing bugs | Jan Leonardi | Edgar Meilinger | 5 | 2 | 5 | 2
51 | Saving schema in Database for excel sheets for import function | User doesn't have to fill schema in every time he starts the program | Amine Amzil | Edgar Meilinger | 5 | 3
52 | Making error messages for important functions | User gets information if something doesn't work | Amine Amzil | Edgar Meilinger | 5 | 1
53 | Making the UI more consistent for greeting screen | Easier to understand for the customer (button names etc.) | Ersan Ünsal | Karsten Rudolf | 5 | 3
54 | Fixing arrowheads | Fixing design of arrowheads | Edgar Meilinger | Jan Leonardi | 5 | 3
55 | Tests
55.1 | Test 1 + documenting bugs | Each group member tests the whole program and it's function after the program is finished and documents bugs | Jan Leonardi | Amine Amzil | 5 | 4
55.2 | Test 2 + documenting bugs | Each group member tests the whole program and it's function after the program is finished and documents bugs | Ersan Ünsal | Jan Leonardi | 5 | 4
55.3 | Test 3 + documenting bugs | Each group member tests the whole program and it's function after the program is finished and documents bugs | Edgar Meilinger | Ersan Ünsal | 5 | 4
55.4 | Test 4 + documenting bugs | Each group member tests the whole program and it's function after the program is finished and documents bugs | Karsten Rudolf | Edgar Meilinger | 5 | 4
55.5 | Test 5 + documenting bugs | Each group member tests the whole program and it's function after the program is finished and documents bugs | Amine Amzil | Karsten Rudolf | 5 | 4
56 | Teammeeting to discuss documented bugs | Each group reports documented bugs at this meeting
56.1 | Fixing Bugs 1 | Each group member will be assigned to fix reported bugs | Jan Leonardi | Amine Amzil | 5
56.2 | Fixing Bugs 2 | Each group member will be assigned to fix reported bugs | Ersan Ünsal | Jan Leonardi | 5
56.3 | Fixing Bugs 3 | Each group member will be assigned to fix reported bugs | Edgar Meilinger | Ersan Ünsal | 5
56.4 | Fixing Bugs 4 | Each group member will be assigned to fix reported bugs | Karsten Rudolf | Edgar Meilinger | 5
56.5 | Fixing Bugs 5 | Each group member will be assigned to fix reported bugs | Amine Amzil | Karsten Rudolf | 5

## Risks
# | Risk | Mitigation action | Responsible | Status
1 | Problems with Group coordination (for example: group member doesn't show up to team meetings ) | Making sure to have a good communication | Karsten Rudolf | Open
2 | People don't work on their assigned tasks (misunderstandings or lazyness) | Making sure every task is in the backlog with the assigned person | Gökhan Ünsal | Open
3 | Miscalculation in time management | Integrating a timeline for each leg / task | Jan Leonardi | Open
4 | Technical difficulties | helping each other out or trying to find a solution as a team | Ersan Ünsal | Open
5 | Language difficulties | helping each other out or trying to find a solution as a team | Karsten Rudolf | Open
6 | Programming difficulties (different skills in programming or less experience) | helping each other out or trying to find a solution as a team (for example: YouTube tutorials, GitHub…) | Jan Leonardi | Closed
7 | A group member is getting ill or has to step back for longterm | Informing the supervisor and ask for further instructions | Edgar Meilinger | Open
8 | Time won't be enough to fulfill the task (if we know it in advance) | Responsible person for task informs team, if the team can't find a solution -> inform supervisor | Edgar Meilinger | Open
9 | The application of Gökhan Ünsal will be declined | workload has to be divided on 5 people | Gökhan Ünsal | Closed
10
11
12
13
14
15
16
17
18
19
20
21

## Time Spent
Summe von Real Effort in h | Spaltenbeschriftungen
Zeilenbeschriftungen | 1 | 2 | 3 | 4 | (Leer) | Gesamtergebnis
Amine Amzil | 6.5 | 12 | 14 | 6 |  | 38.5
Edgar Meilinger | 4 | 7 | 11 | 12 |  | 34
Ersan Ünsal | 6.5 | 11 | 12 | 13 |  | 42.5
Gökhan Ünsal | 0.5 |  |  |  |  | 0.5
Jan Leonardi | 5.5 | 12 | 11 | 11 |  | 39.5
Karsten Rudolf | 11 | 7 | 11 | 11 |  | 40
(Leer)
Gesamtergebnis | 34 | 49 | 59 | 53 |  | 195

## Param (hidden)
Sprint # | Status | Risk Status
1 | Initial | Open
2 | Started | Issue
3 | Cancelled | Closed
4 | Done