## Backlog
Group: A |  |  |  |  | Last update: 28.04.2021
# | Task | Result | Responsible | Support by | Planned for Sprint # | Planned Effort in h | Realized in Sprint # | Real Effort in h
1 | Creating a Discord Server for the Group | Voice communication & Filesharing | Karsten Rudolf | Team | 1 | 5min | 1 | 5min
2 | Creating a WhatsApp Group | Text communication & organising meetings | Edgar Meilinger | Team | 1 | 2min | 1 | 2min
3 | Getting all phone numbers from teammembers for inviting them | Having phone numbers for the WhatsApp Group | Ersan Ünsal | Team | 1 | 0.5 | 1
4 | Setting up a first meeting in Discord | Get to know each other | Jan Leonardi | Team | 1 | 0.5 | 1 | 0.5
5 | What development enviroment do we use ? | all have the same development enviroment | Amine Amzil | Team | 1 | 0.5 | 1 | 0.5
6 | First meeting: What VCS do we use ? | sharing code & version controlling | Ersan Ünsal | Team | 1 | 0.5 | 1 | 0.5
7 | Setting up the VCS (GitHub) | sharing code & version controlling | Ersan Ünsal | Team | 1 | 1 | 1
8 | getting started with node.js, express, GoJS | understanding node.js, express, GoJS | Karsten Rudolf | Team | 1 | 6 | 1
9 | Building a MindMap for the project | Getting an overview for what we have so far (will be extended in the future) | Gökhan Ünsal | Team | 1 | 0.5 | 1 | 0.5
10 | Display Application | Visual overview of the applications and symbols can be move freely on the canvas | Jan Leonardi | Karsten Rudolf | 1 | 5
11 | Application properties | Name, version, description, COTZ, release date, shutdown date, properties window | Edgar Meilinger | Jan Leonardi | 1 | 5
12 | Dataflows | Applications can be connected with directed associations (arrowheads) representing dataflows. Dataflow refers to an data object. | Amine Amzil | Gökhan Ünsal | 1 | 5
13 | Data objects | With following properties: Name, description & personal data ? | Gökhan Ünsal | Edgar Meilinger | 1 | 4
14 | Persistent storage | Application landscape has to be stored persistently e.g. as Database or JSON file | Ersan Ünsal | Karsten Rudolf | 1 | 4
15
16
17
18
19
20
21
22
23

## Risks
# | Risk | Mitigation action | Responsible | Status
1 | Problems with Group coordination (for example: group member doesn't show up to team meetings ) | Making sure to have a good communication | Karsten Rudolf
2 | People don't work on their assigned tasks (misunderstandings or lazyness) | Making sure every task is in the backlog with the assigned person | Gökhan Ünsal
3 | Miscalculation in time management | Integrating a timeline for each leg / task | Jan Leonardi
4 | Technical difficulties | helping each other out or trying to find a solution as a team | Ersan Ünsal
5 | Language difficulties | helping each other out or trying to find a solution as a team | Karsten Rudolf
6 | Programming difficulties (different skills in programming or less experience) | helping each other out or trying to find a solution as a team (for example: YouTube tutorials, GitHub…) | Jan Leonardi
7 | A group member is getting ill or has to step back for longterm | Informing the supervisor and ask for further instructions | Edgar Meilinger
8 | Time won't be enough to fulfill the task (if we know it in advance) | Informing the supervisor and ask for further instructions | Gökhan Ünsal
9
10
11
12
13
14
15
16
17
18
19
20
21

## Param (hidden)
Sprint # | Status | Risk Status
1 | Initial | Open
2 | Started | Issue
3 | Cancelled | Closed
4 | Done